## Activities and Execution
| Activities & Sub-Activities | Duration/Manner | Scope hours are relative to SLF time | Overall Coordination Breakdown | Heritage App Coordinator Time Details | Parties Involved | Objective | Results
Activity 1 | SLF Overall Project Coordination | Jan 2025 - Dec 2026 | 400 hours | 400 hrs based on average of 5 hrs per week over 1.75 years of 80 weeks | -- | SLF | to create a digital platform that changes the way people interact with heritage on Saba | greater engagement and understanding of diverse heritage views, sense of pride and connection to heritage and its central place in Saban society
Activity 2 | APP Content Creation |  | 230 hours | 110 hrs | 230 hrs breakdown
| HAC meetings to determine app content | Beginning Q1 2025 through Q3 2025 |  | 30 hrs: present @ HAC meetings | 30 hrs: 10 HAC meetings @ 3 hrs/meeting incl setup and breakdown/cleanup | SLF, HAC, Heritage Center
| Interviews, scriptwriting, preparing interviewee for professional audio recording, reviewing and providing feedback to Chizzilala on each recording |  |  | 30 hrs: scriptwriting contributions/edits; 45 hrs: present @ contributor preparing | 120 hrs scriptwriting 4 hrs x 30 45 hrs: preparing contributor @ 1.5 hrs x 30 30 hrs: review/respond @ 1 hr/site x 30 225 hrs | SLF, local contributor, Chizzilala
| Partner organization meetings | Q1-Q2 2025 |  | 5 hrs of meetings | 5 hrs meeting w/partner organizations | SLF, Heritage Center, Chizzilala, Culture Department, Tourism
Activity 3 | App Development |  |  | 85 hrs | 480 hrs breakdown:
| Development of app | Initial development to take place in Q1 & Q2 of 2025 | 480 hours, plus volunteer time in meetings and Spotteron development and consultation time | 25 hrs: 25 weeks @ 1 hrs/week | 100 hrs: ideas exchange w/Spotteron (in Switzerland) 25 weeks @ 4 hrs/week | SLF and Spotteron | to create a digital platform that changes the way people interact with heritage on Saba | greater engagement and understanding of diverse heritage views, sense of pride and connection to heritage and its central place in Saban society
| App beta testing | Q2 and Q3 2025 |  | 26 hrs: 26 weeks @ 1 hrs/week | 260 hrs: field testing to ensure functionality; 26 weeks @ 10 hrs/week incl travel time | SLF and various partners | to identify faults or gaps | user friendly app
| App maintenance and updates | Q4 through 2026 with continuous adjustments (hence the need for agile development budget) |  | 34 hrs: 65 weeks @ .5 hr/week | 120 hrs: 60 weeks @ 2 hrs/week-- | SLF and Spotteron | to ensure app meets the needs of the community and users over time | app is a useful resource for audiences on an ongoing basis
Activity 4 | Curation of Audio Component of App | Q2 and Q3 2025 | 160 hours | 30 hrs | 160 hrs | SLF, Heritage Center, Saba Comprehensive School, Chizzilala | to enrich ways to connect with and experience Saba's culture- audio recordings allow even more of the story to be told, in Saban voices, as part of walking tour experiences around the island or when interacting with the platform from afar | incorporating an audio component in the app which features narrations from the people of Saba will significantly enhance user engagement by offering an authentic and immersive experience that deepens the connection to the island's culture. Hearing the stories, traditions, and nuances directly from the voices of Saba's residents will bring the island's rich heritage to life in a way that text and images alone cannot. This personal touch will make the cultural content more relatable and memorable and provide a stronger emotional connection.
|  |  |  | 90 hrs: 3 hrs x 30 audio elements: selection, preservation, maintenance, collection, and archiving of digital assets in consultation with Saba Heritage Center and Community Development/Culture | based on 30 audio elements: 60 hrs: 2hrs/recording incl setup 60 hrs: 1 hrs/recording review/edit/discussion w/Chizzilala 60 hrs: social media documentation and promotion incl FB, IG, YouTube, newsletter, blog
Activity 5 | Development of Supporting Resources for Engagement |  |  | 20 hrs | 172 hrs
| Sticker design to incentivize interaction | initiate Q3 2025 | 60 hours | 20 hrs: general oversight, communications updates | 60 hrs: creation--2hrs/30 stickers after consultation from M2M | SLF and Malachy Multimedia | creating a goal of collecting stickers as you visit cultural highlights on Saba | fostering deeper engagement and a greater appreciation of Saba's culture while also addressing pressing social issues both locally and globally. These resources reinforce the important themes of inclusion, diversity and equity, ensuring that Saba's diverse and varied heritage is fully represented (inclusive of different representations of race, gender, community of origin, religion, ideology, tradition, etc.) showing how these critical issues resonate not just on the island but across the world.
| Creation of visual markers | initiate Q3 2025 | 10 hours |  | 10 hrs: creation--QR codes @ 20 mins/visual marker | SLF, Malachy Multimedia and Imagen Graphics | creating visual markers to promote app usage at various locations
| Creation of a physical, printed map | initiate Q3 2025 | 42 hours |  | 42 hrs: 12 hrs consultation w/M2M + 30 hrs: 1/hr per site location analysis | SLF and Malachy Multimedia | providing an additional tool to assist participants to plan a self-guided cultural tour
| Gamification strategy | initiate Q3 2025 | 60 hours |  | 60 hrs gamification strategy: consultation, research and strategic planning to design gamification approach: key user engagement, reward systems and challenges, location based elements to motivate engatment, client collaboration testing | SLF with Saba Tourism, Culture Department and hospitality industry | using a game to incentivize connecting with various aspects of heritage on Saba
Activity 6 | Development, Design and Execution of Resident Interaction |  |  | 115 hrs | 250 hrs
| Curating resident interaction plan | initiate Q4 2025 | 150 hours | 75 hrs: integral in recruitment, introduction and approach process with residents as managment is 30+-year known resident and the face of the organization | 150 hrs: 5 sessions x 10 residents @ 3 hrs per session. Recruitment and engagement to identirfy and approcah indivuals passionate to share stories, skills and traditions with visitors. Gaining trust takes time to expplain the benefits of meaningful engagment, potential sales opportunities and increased sense of relevance and pride. | SLF with Culture Department and Saba Heritage Center | to provide a modern digital option that facilitates live, dynamic human interactions, allowing participants to connect with and learn directly from community members about Saba's heritage | anecdotal knowledge-sharing takes place between participants and residents about Saba's culture with potential revenue generated for community representatives... Resident interaction promotes meaningful, authentic dialogue while engaging members of the community that are sometimes isolated. These residents are given the opportunity to be included and to serve as valuable representatives of Saba's heritage.
| Coordinating participants with community interactive representative | initiate Q4 2025 then ongoing | 100 hours | 40 hrs: oversite of community interactive represenative and tourism proecess and presence at stakeholder/partner meetings | 100 hrs: development of user-friendly system for setting up interactions via app or in-person appointment consultation to accommodate 'walk-ins' in cooperation with other stakeholders | SLF with Culture Department, Saba Tourism, hopsitality sector
Activity 7 | Monitoring, Evaluation, Assessment, Learning |  |  | 40 hrs | 80 hrs
| Create Project Summary | initiate Q3 2026 | 25 hours | 2 hrs review | 20 hrs | SLF | to share with interested organizations | project replication
| Reporting | interim reports as requested; final reporting Q4 2026 | 25 hours | 34 hrs: review and edits of written reports: interim, annual and final plus financial reporting for interim, annual and final reports | 40 hrs report writing (interim, annual and final) | SLF | to provide qualitative and quantitative metrics and feedback allowing SLF and project sponsors to monitor, evaluate, and improve upon the project | feedback and guidance from interim reporting allows for benchmarking and improvements; final reporting provides financial accountability
| HAC participant surveys | initial surveys Q1 2025 with quarterly surveys thereafter | 5 hours | 2 hrs review | 10 hrs creation and analysis | SLF in cooperation with HAC | to ensure the voice of the community is driving the project | documentation of community-based heritage creation, ensures representation and authenticity of product created
| Review platform metrics | beginning at app rollout and continuing thereafter | 25 hours | 2 hrs review | 10 hrs monitoring and analysis | SLF in cooperation with Spotteron | to gauge response to and usage of app | identify areas that may need improvement, what is most user-friendly/appealing, how this platform is serving the purpose of facilitating greater connection to Saba's heritage
|  |  |  | Total: 400 hrs | Total: 1372 hrs